## 2021-22
VGF UTLIZATION STATEMENT & PHYSICAL PROGRESS OF NEGG PROJECT FY 2021-22
(Amount in Rs crore)
IGGL
Month | Scheduled CAPEX | Actual CAPEX | VGF @ 60 % of capex | Physical Progress %
April'21 | 35.74 | 35.74 | 21.444 | 16.9486 | 165.18
May'21 | 20.97 | 20.97 | 12.582 | 17.9121 | 788.33
June'21 | 143.81 | 122.64 | 73.584 | 18.794
July'21 | 15.8388 | 35.95 | 21.57 | 19.3028
August'21 | 18.8388 | 41.48 | 24.888 | 19.9325
September'21 | 119.9528 | 170.82 | 102.492 | 20.1314
October'21 | 145.3688 | 18.71 | 11.226 | 21.5696
November'21 | 177.5749 | 280.71 | 168.426 | 27.56
December'21 | 249.0487 | 226.49 | 135.894 | 31.71
January'22 | 136.7641 | 107.5371 | 64.5223 | 36.1574
February'22 | 200.3446 | 229.6614 | 137.7968 | 38.84
March'22 | 288.75 | 265.7515 | 159.4509 | 42.9444
Total | 1553.0016 | 1556.46 | 933.876 | 42.9444
VGF received by IGGL during 2021-22: Rs 850 crore

## Sheet2 (hidden)
VGF Utilization based on availability of funds:
(Rs in crore)
Total Capex upto date | 1906.01
Equity received till date | 305
VGF Utilization | 1601.01
Reported Capex upto 31.03.21 | 349.55
VGF Utilization upto 31.03.21 | 209.73
Equity Utilized upto 31.03.21 | 139.82
Equity Utilized during 2021-22 | 165.18
VGF Utilization during 2021-22 | 1391.28
Capex recon | 0