## 2022-23
VGF UTLIZATION STATEMENT & PHYSICAL PROGRESS OF NEGG PROJECT FY 2022-23
(Amount in Rs crore)
IGGL
Month | Scheduled CAPEX | Actual CAPEX | VGF @ 60 % of capex | Physical Progress %
April'22 | 232.0833 | 64.65 | 38.79 | 45.03 | 165.18
May'22 | 232.0833 | 68.1 | 40.86 | 47.68 | 788.33
June'22 | 232.0833 | 165.7 | 99.42 | 49.22
July'22 | 150.4167 | 109.36 | 65.616 | 50.33
August'22 | 150.4167 | 117.32 | 70.392 | 52.43
September'22 | 150.4167 | 117.07 | 70.242 | 53.94
October'22 | 307.25 | 142.23 | 85.338 | 54.96
November'22 | 307.25 | 6.01 | 3.606 | 59.25
December'22 | 307.25 | 423.28 | 253.968 | 61.31
January'23 | 309.29 | 208.29 | 124.974 | 64.19
February'23 | 309.29 | 323.38 | 194.028 | 66.54
March'23 | 309.29 | 575.1784 | 345.107 | 70.01
Total | 2997.12 | 2320.5684 | 1392.341
VGF received by IGGL during 2023-24: Rs 1528.53 crore
VGF received by IGGL during 2022-23: NIL

## Sheet2 (hidden)
VGF Utilization based on availability of funds:
(Rs in crore)
Total Capex upto date | #REF!
Equity received till date | 305
VGF Utilization | #REF!
Reported Capex upto 31.03.21 | 349.55
VGF Utilization upto 31.03.21 | 209.73
Equity Utilized upto 31.03.21 | 139.82
Equity Utilized during 2021-22 | 165.18
VGF Utilization during 2021-22 | #REF!
Capex recon | #REF!