## 2021-22 (hidden)
VGF UTLIZATION STATEMENT & PHYSICAL PROGRESS OF NEGG PROJECT FY 2021-22
(Amount in Rs crore)
IGGL
Month | Scheduled CAPEX | Actual CAPEX | VGF @ 60 % of capex | Physical Progress %
April'21 | 35.74 | 35.74 | 21.444 |  | 165.18
May'21 | 20.97 | 20.97 | 12.582 |  | 788.33
June'21 | 143.81 | 122.64 | 73.584
July'21 | 15.8388 | 35.95 | 21.57
August'21 | 18.8388 | 41.48 | 24.888
September'21 | 119.9528 | 170.82 | 102.492
October'21 | 145.3688 | 18.71 | 11.226
November'21 | 177.5749 | 280.71 | 168.426
December'21 | 249.0487 | 226.49 | 135.894
January'22 | 136.7641 | 107.5371 | 64.5223
February'22 | 200.3446 | 229.6614 | 137.7968
March'22 | 288.75 | 265.7515 | 159.4509
Total | 1553.0016 | 1556.46 | 933.876
VGF received by IGGL during 2021-22: Rs 850 crore

## 2023-24
VGF UTLIZATION STATEMENT & PHYSICAL PROGRESS OF NEGG PROJECT FY 2023-24
(Amount in Rs crore)
IGGL
Month | Scheduled CAPEX | Actual CAPEX | VGF @ 60 % of capex | Physical Progress %
April'23 | 100.8418 | 36.9269 | 22.1562 | 71.7127
May'23 | 100.8418 | 32.74 | 19.644 | 73.9232
June'23 | 100.8418 | 128.5517 | 77.131 | 75.072
July'23 | 121.7809 | 68.41 | 41.046 | 75.7652
August'23 | 121.7809 | 20.72 | 12.432 | 76.1459
September'23 | 121.7809 | 169.4495 | 101.6697 | 76.623
October'23 | 362.681 | 4.892 | 2.9352 | 77
November'23 | 362.681 | 69.7884 | 41.873 | 77.4305
December'23 | 362.681 | 190.907 | 114.5442 | 77.9231
January'24 | 414.4665 | 63.5367 | 38.122 | 78.4698
February'24 | 414.4665 | 111.8782 | 67.1269 | 79.1594
March'24 | 414.4665 | 228.3608 | 137.0165 | 80.398
Total | 2999.3107 | 1126.1613 | 675.6968
VGF received by IGGL during 2023-24: Rs 1043.38 Crores

## Sheet2 (hidden)
VGF Utilization based on availability of funds:
(Rs in crore)
Total Capex upto date | 1906.01
Equity received till date | 305
VGF Utilization | 1601.01
Reported Capex upto 31.03.21 | 349.55
VGF Utilization upto 31.03.21 | 209.73
Equity Utilized upto 31.03.21 | 139.82
Equity Utilized during 2021-22 | 165.18
VGF Utilization during 2021-22 | 1391.28
Capex recon | 0